## ES
Actividades\Semanas | Responsable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Instalar Notas y AIF | Cliente | bar: 1
Definición Funcional | WISE | bar: 1
Realización
Configuración Solución
AIF | WISE | bar: 2
ePayment | WISE | bar: 2
Datos Maestros y Catálogos | Cliente | bar: 2
Construcción
Ajustes Complemento Pago | WISE | bar: 2 to 4
Escenarios Especiales Pagos | WISE
Impresión Complemento Pago | WISE | bar: 5 to 6
Pruebas Unitarias / Ajustes | WISE
Desarrollo SAP Cloud Integration | Cliente | bar: 2 to 6
Configuraciòn SOAMANAGER | Cliente | bar: 2 to 6
Pruebas Integrales/Ajustes | Cliente | bar: 9 to 10
Puesta Marcha y Soporte | WISE | bar: 11 to 12

## EN
Actividades\Semanas | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Install Notes and AIF | Client | bar: 1
Funcional Specification | WISE | bar: 1
Realization
Configuration
AIF | WISE | bar: 2
ePayment | WISE | bar: 2
Master Data | Client | bar: 2
Construction
Enhancement ePayment | WISE | bar: 2 to 4
Special Scenarios | WISE
Printing ePayment | WISE | bar: 5 to 6
Unit Test | WISE
SAP Cloud Integration | Client | bar: 2 to 6
SOAMANAGER Configuration | Client | bar: 2 to 6
Integral Test | Client | bar: 9 to 10
Go Live and Support | WISE | bar: 11 to 12

## Recursos
CFDI Emisión |  |  | 215000 |  |  | 84000 | -60.93%
Recursos | Días Costo | Tarifa Costo | Importe Costo | Dias Venta | Tarifa Venta | Importe Venta | % Rent | Mon
Líder | 5 | 3000 | 15000 | 2 | 4500 | 9000 | -40% | MXN
Funcional | 40 | 3000 | 120000 | 5 | 4500 | 22500 | -81.25% | MXN
ABAP 1 | 40 | 2000 | 80000 | 15 | 3500 | 52500 | -34.38% | MXN
ABAP 2 | 0 | 2000 | 0 | 0 | 3500 | 0 | #DIV/0! | MXN
CFDI Pagos |  |  | 295000 |  |  | 629000 | 113.2%
Recursos | Días Costo | Tarifa Costo | Importe Costo | Dias Venta | Tarifa Venta | Importe Venta | % Rent | Mon
Líder | 5 | 3000 | 15000 | 2 | 4500 | 9000 | -40% | MXN
Funcional | 40 | 3000 | 120000 | 60 | 4500 | 270000 | 125% | MXN
ABAP 1 | 40 | 2000 | 80000 | 60 | 3500 | 210000 | 162.5% | MXN
ABAP 2 | 40 | 2000 | 80000 | 40 | 3500 | 140000 | 75% | MXN
CFDI Comercio Exterior |  |  | 215000 |  |  | 84000 | -60.93%
Recursos | Días Costo | Tarifa Costo | Importe Costo | Dias Venta | Tarifa Venta | Importe Venta | % Rent | Mon
Líder | 5 | 3000 | 15000 | 2 | 4500 | 9000 | -40% | MXN
Funcional | 40 | 3000 | 120000 | 5 | 4500 | 22500 | -81.25% | MXN
ABAP 1 | 40 | 2000 | 80000 | 15 | 3500 | 52500 | -34.38% | MXN
ABAP 2 | 0 | 2000 | 0 | 0 | 3500 | 0 | #DIV/0! | MXN
CFDI Leyendas Fiscales |  |  | 215000 |  |  | 84000 | -60.93%
Recursos | Días Costo | Tarifa Costo | Importe Costo | Dias Venta | Tarifa Venta | Importe Venta | % Rent | Mon
Líder | 5 | 3000 | 15000 | 2 | 4500 | 9000 | -40% | MXN
Funcional | 40 | 3000 | 120000 | 5 | 4500 | 22500 | -81.25% | MXN
ABAP 1 | 40 | 2000 | 80000 | 15 | 3500 | 52500 | -34.38% | MXN
ABAP 2 | 0 | 2000 | 0 | 0 | 3500 | 0 | #DIV/0! | MXN
CFDI Traslados |  |  | 215000 |  |  | 84000 | -60.93%
Recursos | Días Costo | Tarifa Costo | Importe Costo | Dias Venta | Tarifa Venta | Importe Venta | % Rent | Mon
Líder | 5 | 3000 | 15000 | 2 | 4500 | 9000 | -40% | MXN
Funcional | 40 | 3000 | 120000 | 5 | 4500 | 22500 | -81.25% | MXN
ABAP 1 | 40 | 2000 | 80000 | 15 | 3500 | 52500 | -34.38% | MXN
ABAP 2 | 0 | 2000 | 0 | 0 | 3500 | 0 | #DIV/0! | MXN
Carta Porte |  |  | 51000 |  |  | 124000 | 143.1%
Recursos | Días Costo | Tarifa Costo | Importe Costo | Dias Venta | Tarifa Venta | Importe Venta | % Rent | Mon
Líder | 2 | 3000 | 6000 | 2 | 4500 | 9000 | 50% | MXN
Funcional | 5 | 3000 | 15000 | 10 | 4500 | 45000 | 200% | MXN
ABAP 1 | 15 | 2000 | 30000 | 20 | 3500 | 70000 | 133.3% | MXN
ABAP 2 | 0 | 2000 | 0 | 0 | 3500 | 0 | #DIV/0! | MXN